## 03-2012 Burndown
-1
Planning
Day | Commitment | Projected | Remaining | Injected | Mike | Ben | Debra | Sonal | Amy | Tim | Total | Variance
2012-03-12 | 255 | 237 | 235 | 0 | 6 | 6 | 1 | 2 | 2 | 1 | 18 | 0%
2012-03-13 | 255 | 222 | 230 | 0 | 6 | 6 | 2 | 0 | 0 | 1 | 15 | 0%
2012-03-14 | 255 | 201 | 222 | 0 | 6 | 6 | 1 | 2 | 5 | 1 | 21 | 0%
2012-03-15 | 255 | 186 | 208 | 0 | 6 | 6 | 2 | 0 | 0 | 1 | 15 | 0%
2012-03-16 | 258 | 169.8118 | 190 | 3 | 6 | 6 | 1 | 2 | 0 | 1 | 16 | 1.176%
2012-03-19 | 258 | 151.6 | 168 | 0 | 6 | 6 | 1 | 2 | 2 | 1 | 18 | 1.176%
2012-03-20 | 258 | 136.4235 |  |  | 6 | 6 | 2 | 0 | 0 | 1 | 15 | 1.176%
2012-03-21 | 258 | 115.1765 |  |  | 6 | 6 | 1 | 2 | 5 | 1 | 21 | 1.176%
2012-03-22 | 258 | 100 |  |  | 6 | 6 | 2 | 0 | 0 | 1 | 15 | 1.176%
2012-03-23 | 258 | 83.8118 |  |  | 6 | 6 | 1 | 2 | 0 | 1 | 16 | 1.176%
2012-03-26 | 258 | 65.6 |  |  | 6 | 6 | 1 | 2 | 2 | 1 | 18 | 1.176%
2012-03-27 | 258 | 50.4235 |  |  | 6 | 6 | 2 | 0 | 0 | 1 | 15 | 1.176%
2012-03-28 | 258 | 29.1765 |  |  | 6 | 6 | 1 | 2 | 5 | 1 | 21 | 1.176%
2012-03-29 | 258 | 14 |  |  | 6 | 6 | 2 | 0 | 0 | 1 | 15 | 1.176%
2012-03-30 | 258 | -2.1882 |  |  | 6 | 6 | 1 | 2 | 0 | 1 | 16 | 1.176%
Total |  |  |  |  | 90 | 90 | 21 | 18 | 21 | 15 | 255 | 0.3922%
On March 3rd, 3 hours of work was added to the TFS Environment user story.

## 03-2012 Sprint Backlog
ID | User Story / Epic | Estimate | Sprint | Priority
| As a HOST Parent, I would like to receive an email once I Submit the OST Enrollment Form with a copy of the enrollment form attached to it. | 15 | 1 | 1
| Environment Setup - Team Foundation Server | 5 | 1 | 2
| As a HOST Parent, I need to be able to search enrollment information for my child. | 15 | 1 | 3
| As a HOST Parent, I need to be able to enter/update enrollment information for my child. | 25 | 1 | 4
| As a Fees User, I would like to associate a previous fee account to a participant if they attended the same site both years. | 8 | 1 | 5
| As a HOST Staff member, I need to be able to review submitted enrollment forms. | 42 | 1 | 6
| As an SES District Admin, I would like to view denied invoicing attendances. | 47 | 1 | 7
| As a District Admin, I do not want Supp Service users to be able to modify Staff Education Levels and Background Checks after I approve them. | 12 | 1 | 8
| As a SES district user, I need the Referral Date (the date the student was registered in SES) to be added to the FL Export report, so that I can report this information to the State. | 12 | 1 | 9
| As a OST staff member, I need to be notified when new participants are placed in my site so that I know that they are ready to receive services. | 10 | 1 | 10
| As a SES Provider, I need to receive all messages generated from the auto transfer process. | 16 | 1 | 11
| Environment Setup - Test Solution / Test Machine | 9 | 1 | 12
| Environment Setup - Mobile UI Testing Box | 6 | 1 | 13
| As a HOST parent, I need to be able to view the on-line enrollment form in my selected language. | 25 | 1 | 14
| When registering students from a prior term and the "increase grade level by" field was blank, an error displayed. | 6 | 1 | 15
| Demo (prep, meeting, feedback) | 5 | 1 | 16
| Total Hours for Sprint | 258
|  | Sprint | Hours | Capacity
|  | 3/12 - 3/30 | 258 | 255
|  | Total | 258 | 255
Note on C3: Robert Carlson: 3 hours injected on 3/19

## Dropdowns (hidden)
1 - Critical
2 - High
3 - Normal
4 - Low
Not Started
In Progress
Completed