## Team
| Sprint Time [ST] | Commit Sprint Time [CST] | Commitment Loss [CL]
Team Member | [Hours] | [Hours] | [Hours]
| 480 | 440 | 40 | Totals [Hours]
Team Member 1 | 160 | 160 | 0
Team Member 2 | 160 | 120 | 40
Team Member 3 | 160 | 160 | 0
Totals [Hours] | 480 | 440 | 40 | Totals [Hours]
XVelocity (velocity using criteria) |  | [%] | Relevance
MVelocity (Management: Delivery / Sprint Time) |  | 79.1667 | Management
KVelocity (Knowledge: Delivery / Estimation) |  | 82.6087 | Biz.Process & Technology Knowledge
EVelocity (Efficiency: Delivery / Commitment) |  | 86.3636 | Team Efficiency

## Tasks
| Task Value Time [TVT] | Delivered Value Time [DVT] |  | Lost Value Time [LVT]
| [Hours] | [Hours] | [%] | [Hours]
| 460 | 380 |  | 80 | Totals
Tasks / Priority | Estimated | Delivered
Tasks1 | 100 | 90 | 90 | 10
Tasks2 | 200 | 170 | 85 | 30
Tasks3 | 50 | 35 | 70 | 15
Tasks4 | 20 | 10 | 50 | 10
Tasks5 | 50 | 50 | 100 | 0
Tasks6 | 10 | 10 | 100 | 0
Tasks7 | 30 | 15 | 50 | 15
Totals | 460 | 380 |  | 80 | Totals
Commitment Loss [CL] | 40 |  |  | +
Estimation Loss [EL] | 20 |  |  |  |  | `
Planned Loss [PL] | 20 |  | + | 100 | Total Lost [TL]